## WBS_Zam
Project Name |  |  |  | Created By
Filename | Details_WBS.xlsx |  |  | Created Date |  | 2025-01-13
Remarks |  |  |  | Updated By
|  |  |  | Updated Date |  |  |  |  | 1 | [6 empty] | 2 | [6 empty] | 3 | [6 empty] | 4 | [6 empty] | 5 | [6 empty] | 6 | [6 empty] | 7 | [6 empty] | 8
Project Start Date | 01/13/2025 |  | Overall Progress
 | time axis 2023-11-06 to 2023-12-31
Item No. | Task Description | Assigned To | Progress | Plan Start | Plan End | Actual Start | Actual End | Remarks
1 | WBS001_UI | Jaharuddin, Jannatil Anwar Bin | To do | 01/13/2025 | 01/17/2025
2 | WBS002_UI | Jaharuddin, Jannatil Anwar Bin | To do | 01/20/2025 | 01/24/2025
3 | WBS003_UI | Jaharuddin, Jannatil Anwar Bin | To do | 01/27/2025 | 01/31/2025
4 | WBS001PRO001_CreateLoginFunction | Jaharuddin, Jannatil Anwar Bin | To do | 01/13/2025 | 01/27/2025
5 | WBS001PRO003_CreateRegisterFunction | Jaharuddin, Jannatil Anwar Bin | To do | 02/03/2025 | 02/17/2025
6 | WBS004_UI - Logout Confirmation Screen | Nuramira Binti Ahmad Mahmud | To do | 01/13/2025 | 01/15/2025
7 | WBS001PRO002_CreateLogoutFunction | Muhammad Izzun Mustaqim Bin Ismahdi | To do | 01/13/2025 | 01/17/2025
8 | WBS001PRO004_CreatePasswordResetFunction | Muhammad Izzun Mustaqim Bin Ismahdi | To do | 01/20/2025 | 01/24/2025
9 | Code Review - WBS001PRO001_CreateLoginFunction | Muhammad Izzun Mustaqim Bin Ismahdi | To do | 01/29/2025 | 01/31/2025
10 | Code Review - WBS001PRO003_CreateRegisterFunction | Muhammad Izzun Mustaqim Bin Ismahdi | To do | 02/19/2025 | 02/21/2025
11 | Testing - Login/Registration | Nuramira Binti Ahmad Mahmud | To do | 01/29/2025 | 02/01/2025
12 | Testing - Logout functionality | Nur Ain Binti Mahamad Salleh | To do | 01/20/2025 | 01/22/2025
13 | Integration Testing - UI and Backend | Nur Ain Binti Mahamad Salleh & Nuramira Binti Ahmad Mahmud | To do | 02/03/2025 | 02/07/2025
14 | User Acceptance Testing (UAT) - All Features | All Team Members | To do | 02/19/2025 | 03/01/2025
15 | Final Code Review and Refinements | Jaharuddin, Jannatil Anwar Bin | To do | 03/04/2025 | 03/10/2025
16 | Deployment Preparation | Jaharuddin, Jannatil Anwar Bin | To do | 03/11/2025 | 03/13/2025

## Setting (hidden)
TBL_Member | Plan Start Date | 1
Member | Plan End Date | 2
Zamzarina | Plan Same Date | 0
Dayalan
Aziana
Arief | J9
All
GI68